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Consulting Services Agreement
Cascade Partners and Aldergrove Manufacturing
This agreement records the terms under which Cascade Partners will deliver the engagement known internally as [REDACTED]. It is issued by Dana Whitfield, Engagement Lead, and countersigned by Marcus Oyelaran.

1. Scope of work
Cascade Partners will review the current order-to-cash process at Aldergrove Manufacturing, identify the constraints limiting throughput, and deliver a prioritised remediation plan with an implementation roadmap.
The engagement covers the following workstreams:
· Process discovery across order intake, fulfilment and invoicing
· Data analysis of eighteen months of transaction history
· Constraint modelling and options appraisal
· A remediation roadmap with sequencing and effort estimates
2. Schedule
The vendor shall deliver the completed remediation plan by 30 June 2026.
Interim findings will be presented at the end of each workstream. The client will provide feedback within five working days of each presentation.
2.1 Milestones
	Milestone
	Owner
	Workstream

	Discovery complete
	Dana Whitfield
	Process discovery

	Analysis complete
	Marcus Oyelaran
	Data analysis

	Draft roadmap
	Dana Whitfield
	Constraint modelling

	Final plan delivered
	Dana Whitfield
	Remediation roadmap



3. Fees
The total contract value is 120,000 USD, payable in three instalments.
Invoices are issued on milestone acceptance and are payable within thirty days. Expenses are billed at cost and require prior written approval.
4. Change control
Either party may request a change to the scope, schedule or fees. A change takes effect only once both parties have signed a written change note recording its impact on each of the three.
Where a requested change would delay an agreed milestone, the vendor will say so in the change note before the client is asked to approve it.
5. Intellectual property
The client owns the deliverables listed in the statement of work on payment in full. Cascade Partners retains ownership of the methods, templates and tools it brings to the engagement, and grants the client a perpetual, non-exclusive licence to use them to the extent they are embedded in a deliverable.
6. Data protection
The vendor processes client data only to the extent needed to deliver the engagement, and only on documented instructions from the client. Personal data encountered during discovery is pseudonymised before analysis.
Transaction records shared for analysis are deleted or returned within thirty days of the final deliverable being accepted.
7. Confidentiality
Both parties will treat the existence and content of [REDACTED] as confidential. Neither party will disclose the other's confidential information to a third party without prior written consent, except where required by law.
This clause survives termination of the agreement by five years.
8. Liability
Neither party excludes liability for death or personal injury caused by negligence, or for fraud. Subject to that, each party's total liability is capped at the total contract value.
Neither party is liable for indirect or consequential loss, including loss of profit, revenue or anticipated savings.
9. Termination
Either party may terminate on thirty days' written notice. On termination the client pays for work completed and accepted up to the termination date, together with any expenses already committed and not recoverable.
10. Acceptance
Deliverables are accepted once they pass the acceptance criteria agreed at the start of each workstream. Acceptance will not be unreasonably withheld.

Questions about this agreement should go to hello@cascadepartners.example.
https://cascadepartners.example
11. Signatures
Signed for Cascade Partners: ____________________   Date: ____________

Signed for Aldergrove Manufacturing: ____________________   Date: ____________
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